# Launch Plan  for Forming the PMI Agile Forum

Launch Milestone Chart for Forming Communities

|  | Milestone | Description | Date | Status |
| --- | --- | --- | --- | --- |
| 1 | Submitted to VCP | Community concept is submitted to VCP for evaluation | 22 Oct 2007 | Completed |
| 2 | Chartered by VCP | VCP approves the concept and charters a project to launch the community | 18 Oct 2008 | Completed |
| 3 | Community Placed in Formation Queue | Upon chartering of the launch project, PMI: Places community in formation queue Assigns an account manager and VCAG liaison Arranges teleconference between community champions, PMI and VCAG member Recognizes community as “Forming Community” | 18 Oct 2008 | Completed |
| 4 | Steering Team Identified | Community champions select a Steering Team to guide the formation project | Jan 1 2009 | Completed |
| 5 | Steering Team Approved | Steering team members must complete, sign, and return to PMI the following documents: Use of Member Data Agreement Confidentiality Agreement Conflict of Interest Questionnaire | Jan 7 2009 | Completed |
| 5 | Communication and Business Planning | PMI and community communicate formation status to membership. PMI provides templates and instruction for business planning. | Jan 7 2009 | Completed |
| 6 | Develop Year 1 Business Plan | Business plan template must be completed (for Year 1 ONLY) by steering team, with assistance from PMI market research and VCAG liaison. | 1 Mar 2009 | Completed |
| 7 | Documentation Submitted | Community must complete, sign, and return to PMI the Year 1 Business Plan | 1 Apr 2009 | Completed |
| 8 | Community Approved | PMI executive team approves the community for official launch | 15 Apr 2009 | Pending |
| 9 | Resources Provided | PMI provides the community with access to administrative, financial, and technology resources | 17 Apr 2009 | Pending |
| 10 | Soft Launch | Community launches preliminary services to select focus group | 15 May 2009 | Pending |
| 11 | Formal Launch | At PMI Global Congress EMEA, PMI formally announces community to full membership Community begins executing against Year 1 Business Plan | 30 Jun 2009 | Pending |